## Schedule
Date | Tasks | Teammates (5) | Teammates (6)
2022-01-31 | Sprint2 Planning | All
2022-02-01 | Sprint2 Planning Due |  | All
Get clarification on "Backlog" features
2022-02-02
2022-02-03 | Choose Game Genre |  | All
2022-02-04
2022-02-05 | meeting? |  | All
2022-02-06
2022-02-07
2022-02-08 | Tasks 1-4 First Pass | Boru and Leigh
| Tasks 5-6 First Pass | Isaac
| Tasks 7-8 | Keyi | Jianlin and Keyi
| Tasks 9-10 | Jianlin | Daniel
2022-02-09
2022-02-10 | Reevaluate |  | All
2022-02-11
2022-02-12 | Finish Functionality |  | All
| Complete 1 set of code reviews |  | All
2022-02-13 | Refine and Refactor |  | All
2022-02-14 | meeting?
2022-02-15
2022-02-16 | Finish all refactoring |  | All
| Complete 2nd set of code review |  | All
2022-02-17
2022-02-18 | Finish documentation and administrative tasks |  | All
submit project
2022-02-19 | Sprint2 Due at Noon

## Tasks
D U E 1 1 : 5 9 P M 2 / 1 |  |  |  | C O D I N G T A S K S |  |  |  |  | N O N - C O D I N G T A S K S
PLANNING | Tips | Player | Block/Obstacle Controls | Item Controls | Enemy/NPC controls | Other Controls | General Tasks? | README | Task Tracking | Code Reviews & Reflection
Have all team members been added to GitHub? | Put a high emphasis on readability and simplicity in the first half of the sprint | Task1 - Leigh | Task4 - Leigh & Boru? | Task5 - Isaac | Task7 - Keyi | Task9 - Jianlin and Daniel | Task10 - Jianlin | Create document | Post in #edits-log in the discord what and when you start on a feature | Each Member: Review one class and have one of their classes reviewed, with a focus on readability
Due date has been added | Then, when refactoring, focus on maintainability | Implement moving player | Implement block types to cycle through | Implement cycling through which item is visible | Implement enemy types and ability to cycle through them | Use "Q" to quit | Implement commands | program controls | Create "estimated task time remaining" feature and keep this updated | Each Member: Review one class and have one of their classes reviewed, with a focus on maintainability
Backlog features? (Optimizing sprint0 content?) |  | Task2 - Boru | Stationary, no interaction with other objects | Items must move | NPC can move | use "R" to reset the program to its initial state | Implement controllers | descriptions of known bugs | Check off tasks when they're done | Write brief reflection
Assign tasks of equal effort to each team member |  | Implement swinging sword | Create block class(es) | Items must animate | NPC can animate | Implement all keybinds | Implement keyboard input | explain any unrequired processes or tools (explain extra stuff) |  | burndown chart??
Does one person create all interfaces, or do the implementors choose when to use interfaces? |  | Implement item select |  | No interaction with other objects | State Machine?? | "WASD" and arrow keys move player | Code metrics????
|  | Implement player damage |  | Task6 - Isaac | Task8 - Daniel?? | "N" and "Z" swing player sword | submit project
|  | Task3 - Boru & Leigh |  | Create item classes | Create enemy classes | Number keys player item select
|  | Create player class |  |  | NPC can fire projectiles | "E" damages player
|  | Create player state transitions |  |  |  | "T" and "Y" cycling for blocks
"U" and "I" for item cycling
"O" and "P" for cycling enemies