## Schedule
2022-02-22 | Sprint 3 Planning due | Midterms | TASKS IN PROGRESS | TEAM MEMBER(S) | START DATE | ESTIMATED TIME | ACTUAL TIME | END DATE
2022-02-23 |  |  | Refining Sprint 2 | Leigh | 2022-02-23 | 5:00
2022-02-24
2022-02-25 |  | Keyi
2022-02-26
2022-02-27 |  | Boru
2022-02-28
2022-03-01 |  | Jianlin, Leigh
2022-03-02
2022-03-03 | First Pass due | Leigh (eh)
2022-03-04 |  | Jianlin
2022-03-05
2022-03-06
2022-03-07 | Finish Functionality; Do 1 set of code reviews
2022-03-08
2022-03-09 | Finish Refactoring; Do 2nd set of code reviews
2022-03-10 |  | Isaac
2022-03-11 | Finish administrative tasks | Keyi
2022-03-12 | Sprint 3 due at Noon
2022-03-13
2022-03-14
2022-03-15
2022-03-16
2022-03-17 | Sprint 3 Peer Reviews Due

## Tasks
PLANNING & DOCUMENTATION | REFINING SPRINT 2 - Leigh & Isaac? | COLLISION - GENERAL-Boru | GAME OBJECT MANAGER - Isaac | LEVEL LOADING - Jianlin & Keyi & Leigh | LEVEL CREATION - Leigh
-put all items on schedule | >Fix player movement | Implement Collision Handling | Create Game Object Manager | Create rooms/screens/loading zones | *Research Legend of Zelda First Dungeon
-how will we enforce this schedule | >Finish sprites? | >Collision Detection |  | -use the mouse controller to switch rooms | Implement all rooms
>Should we include sprite-making on the schedule? -No, extra stuff to add in later | >Change Execute to take no parameters and be able to pass in any object/player into the keyboard |  |  | -could be through a map | Add testing room with all objects
1 set of code reviews | >Player stops moving when they attack? |  |  | -or, through an ordered list | - be able to reach test room quickly
2nd set of code reviews | >Move all sprite declarations from Game1 into the Sprite Factory |  |  | -we could do vertical levels of a pyramid
README | > update player damage state |  |  | Create XML level database
Analyse code metrics |  | COLLISION - STATIC-Boru | PLAYER MOVEMENT - Daniel
Sprint Reflection |  | -player v. item | Optional: Create Gamepad class
Peer Review Spreadsheet |  | -player/enemy v. block | -arrow keys and WASD for player movement
Make sprint3 branch, THEN individual branches from there |  |  | -eventually, data-drive this so controls can be set by the user
Submit project |  |  | -settings page?
COLLISION - MOVING-Boru
- throwables
-player vs enemy
melee attack: range?